## Summary
| 1500W AC | 3000 W AC | Installed 1500W AC | Installed 3000W AC | Remaining 1500W AC | Remaining 3000W AC | Remaining 1500 W Sites | Remaining 3000 W Sites
Region 4 | 1 | 138 | 0 | 0 | 1 | 138 | 0
Region 5 | 0 | 146 | 0 | 0 | 0 | 146 | 0 | 0
Region 6 | 16 | 0 | 0 | 0 | 16 | 0 | 0 | 0
Total | 17 | 284 | 0 | 0 | 17 | 284 | 0 | 0
| 301 |  | 0 |  | 301 |  | 0

## Tracking Sheet
Site ID | Latitude | Longitude | Scope Of Work (QTY) | Count Of Installed ACs | Region | AC Brand | Scope Status | Installation Date
ABH0006 | 18.2025 | 42.5143 | 1 | 0 | Region_6 | ZTE 1500W | Open
ABH0028 | 18.2244 | 42.5025 | 1 | 0 | Region_6 | ZTE 1500W | Open
ABH0029 | 18.2503 | 42.6293 | 1 | 0 | Region_6 | ZTE 1500W | Open
KMS0033 | 18.2975 | 42.7298 | 1 | 0 | Region_6 | ZTE 1500W | Open
KMS0035 | 18.2914 | 42.754 | 1 | 0 | Region_6 | ZTE 1500W | Open
KMS0040 | 18.3072 | 42.7392 | 1 | 0 | Region_6 | ZTE 1500W | Open
KMS0051 | 18.3117 | 42.7279 | 1 | 0 | Region_6 | ZTE 1500W | Open
ABH0122 | 18.2296 | 42.527 | 1 | 0 | Region_6 | ZTE 1500W | Open
ARF0078 | 18.202 | 42.8188 | 1 | 0 | Region_6 | ZTE 1500W | Open
KMS0037 | 18.2616 | 42.7651 | 1 | 0 | Region_6 | ZTE 1500W | Open
KMS0043 | 18.2501 | 42.7796 | 1 | 0 | Region_6 | ZTE 1500W | Open
KMS0044 | 18.2421 | 42.766 | 1 | 0 | Region_6 | ZTE 1500W | Open
ARF0075 | 18.1377 | 42.848 | 1 | 0 | Region_6 | ZTE 1500W | Open
KHS0929 | 18.7678 | 42.9193 | 1 | 0 | Region_6 | ZTE 1500W | Open
BKR0044 | 19.9202 | 41.5615 | 1 | 0 | Region_6 | ZTE 1500W | Open
SUR0145 | 18.0813 | 43.1326 | 1 | 0 | Region_6 | ZTE 1500W | Open
JED2322 | 21.44849 | 39.2546 | 1 | 0 | Region_4 | ZTE 1500W | Open
JED0894 | 21.5963 | 39.1458 | 1 | 0 | Region_4 | Envicool 3000W | Open
HHR0873 | 21.3656 | 39.6981 | 1 | 0 | Region_5 | Envicool 3000W | Open
MAK0195 | 21.5392 | 39.9398 | 1 | 0 | Region_5 | Envicool 3000W | Open
HHR0429 | 21.3332 | 39.653 | 1 | 0 | Region_5 | Envicool 3000W | Open
MAK0654 | 21.3271 | 39.6888 | 1 | 0 | Region_5 | Envicool 3000W | Open
AKR0971 | 21.7547 | 40.0643 | 1 | 0 | Region_5 | Envicool 3000W | Open
HHR0872 | 21.3556 | 39.6829 | 1 | 0 | Region_5 | Envicool 3000W | Open
HAS0724 | 21.2464 | 39.936 | 1 | 0 | Region_5 | Envicool 3000W | Open
MAK0322 | 21.4158 | 39.8666 | 1 | 0 | Region_5 | Envicool 3000W | Open
MAK0839 | 21.427579 | 39.830521 | 1 | 0 | Region_5 | Envicool 3000W | Open
JED0873 | 21.8197 | 39.2587 | 1 | 0 | Region_4 | Envicool 3000W | Open
YLM0776 | 20.8740316 | 40.1742625 | 1 | 0 | Region_4 | Envicool 3000W | Open
JED0235 | 21.4256 | 39.3122 | 1 | 0 | Region_4 | Envicool 3000W | Open
JED0155 | 21.523 | 39.167 | 1 | 0 | Region_4 | Envicool 3000W | Open
MAk0689 | 21.4748 | 40.028 | 1 | 0 | Region_5 | Envicool 3000W | Open
MAK0854 | 21.5263685 | 39.8810958 | 1 | 0 | Region_5 | Envicool 3000W | Open
QUB0352 | 21.7505 | 39.9811 | 1 | 0 | Region_5 | Envicool 3000W | Open
MAK0464 | 21.6908 | 39.8186 | 1 | 0 | Region_5 | Envicool 3000W | Open
MAK0250 | 21.1153 | 39.9375 | 1 | 0 | Region_5 | Envicool 3000W | Open
MAK0002 | 21.4841 | 40.0252 | 1 | 0 | Region_5 | Envicool 3000W | Open
AKR0134 | 21.64585 | 40.09036 | 1 | 0 | Region_5 | Envicool 3000W | Open
MAk0677 | 21.4755 | 39.9831 | 1 | 0 | Region_5 | Envicool 3000W | Open
ISH0350 | 21.7536 | 39.9087 | 1 | 0 | Region_5 | Envicool 3000W | Open
MAK0228 | 21.4888 | 40.0114 | 1 | 0 | Region_5 | Envicool 3000W | Open
BIK0770 | 21.0862 | 39.9112 | 1 | 0 | Region_5 | Envicool 3000W | Open
MAk0675 | 21.2601 | 39.9569 | 1 | 0 | Region_5 | Envicool 3000W | Open
MAK0781 | 21.5526 | 39.8215 | 1 | 0 | Region_5 | Envicool 3000W | Open
MAK0652 | 21.3179 | 39.7057 | 1 | 0 | Region_5 | Envicool 3000W | Open
QUR0342 | 21.3421 | 40.1846 | 1 | 0 | Region_5 | Envicool 3000W | Open
JED0800 | 21.642 | 39.1662 | 1 | 0 | Region_4 | Envicool 3000W | Open
YLM0391 | 20.872813 | 40.3794441 | 1 | 0 | Region_4 | Envicool 3000W | Open
GMK0046 | 20.20876 | 40.453527 | 1 | 0 | Region_4 | Envicool 3000W | Open
JED0948 | 21.5433 | 39.1747 | 1 | 0 | Region_4 | Envicool 3000W | Open
JED0016 | 21.3159 | 39.2113 | 1 | 0 | Region_4 | Envicool 3000W | Open
MAK0045 | 21.4569 | 40.0076 | 1 | 0 | Region_5 | Envicool 3000W | Open
MAK0144 | 21.4801 | 39.9967 | 1 | 0 | Region_5 | Envicool 3000W | Open
MAK0187 | 21.4085 | 39.7883 | 1 | 0 | Region_5 | Envicool 3000W | Open
MKTF0932 | 21.1551 | 39.9042 | 1 | 0 | Region_5 | Envicool 3000W | Open
QUR0340 | 21.3917 | 40.1813 | 1 | 0 | Region_5 | Envicool 3000W | Open
MAK0684 | 21.2966 | 39.6813 | 1 | 0 | Region_5 | Envicool 3000W | Open
MAK0230 | 21.3844 | 39.8213 | 1 | 0 | Region_5 | Envicool 3000W | Open
MAK0274 | 21.4632 | 39.956 | 1 | 0 | Region_5 | Envicool 3000W | Open
MAK0619 | 21.4445 | 39.966 | 1 | 0 | Region_5 | Envicool 3000W | Open
MAK0732 | 21.4586 | 40.0275 | 1 | 0 | Region_5 | Envicool 3000W | Open
MAK0515 | 21.4465 | 39.8291 | 1 | 0 | Region_5 | Envicool 3000W | Open
MAK2090 | 21.3573 | 39.828 | 1 | 0 | Region_5 | Envicool 3000W | Open
MAK2096 | 21.3989 | 39.8026 | 1 | 0 | Region_5 | Envicool 3000W | Open
HAS0712 | 21.2843 | 39.9309 | 1 | 0 | Region_5 | Envicool 3000W | Open
HRT0786 | 21.1868 | 40.1381 | 1 | 0 | Region_5 | Envicool 3000W | Open
MAK0833 | 21.3472 | 39.8052 | 1 | 0 | Region_5 | Envicool 3000W | Open
MSK0365 | 21.6969 | 40.3031 | 1 | 0 | Region_5 | Envicool 3000W | Open
GMQ0151 | 20.023461 | 40.771736 | 1 | 0 | Region_4 | Envicool 3000W | Open
SIR0125 | 20.436396 | 40.6948705 | 1 | 0 | Region_4 | Envicool 3000W | Open
TAF2404 | 21.2273 | 40.3973 | 1 | 0 | Region_4 | Envicool 3000W | Open
HAJ0295 | 21.3555 | 39.9865 | 1 | 0 | Region_5 | Envicool 3000W | Open
HAJ0367 | 21.3906 | 39.8971 | 1 | 0 | Region_5 | Envicool 3000W | Open
JED0041 | 21.6434 | 39.1306 | 1 | 0 | Region_4 | Envicool 3000W | Open
JED0143 | 21.4848 | 39.2216 | 1 | 0 | Region_4 | Envicool 3000W | Open
JED0282 | 21.6146 | 39.1422 | 1 | 0 | Region_4 | Envicool 3000W | Open
JED0299 | 21.6503 | 39.2423 | 1 | 0 | Region_4 | Envicool 3000W | Open
MLJI0377 | 20.6712 | 40.5523 | 1 | 0 | Region_4 | Envicool 3000W | Open
JED2506 | 21.770409 | 39.208347 | 1 | 0 | Region_4 | Envicool 3000W | Open
JED2168 | 21.5682 | 39.2049 | 1 | 0 | Region_4 | Envicool 3000W | Open
JED0869 | 21.7025 | 39.2114 | 1 | 0 | Region_4 | Envicool 3000W | Open
TAF2343 | 21.2867 | 40.4096 | 1 | 0 | Region_4 | Envicool 3000W | Open
JED0141 | 21.5884 | 39.1571 | 1 | 0 | Region_4 | Envicool 3000W | Open
TAF0145 | 21.2731 | 40.4333 | 1 | 0 | Region_4 | Envicool 3000W | Open
JED2146 | 21.583664 | 39.175813 | 1 | 0 | Region_4 | Envicool 3000W | Open
JED0816 | 21.3779 | 39.3079 | 1 | 0 | Region_4 | Envicool 3000W | Open
NNL0084 | 20.537 | 40.548 | 1 | 0 | Region_4 | Envicool 3000W | Open
JED0956 | 21.7759 | 39.0904 | 1 | 0 | Region_4 | Envicool 3000W | Open
JED0896 | 21.7181 | 39.252 | 1 | 0 | Region_4 | Envicool 3000W | Open
JED0768 | 21.5886 | 39.1434 | 1 | 0 | Region_4 | Envicool 3000W | Open
JED2864 | 21.5804 | 39.21341 | 1 | 0 | Region_4 | Envicool 3000W | Open
JED0142 | 21.61 | 39.1534 | 1 | 0 | Region_4 | Envicool 3000W | Open
JED0844 | 21.6847 | 39.2122 | 1 | 0 | Region_4 | Envicool 3000W | Open
SIR0166 | 20.3554 | 40.7983 | 1 | 0 | Region_4 | Envicool 3000W | Open
JED0960 | 21.5151 | 39.2312 | 1 | 0 | Region_4 | Envicool 3000W | Open
JED2066 | 21.5903 | 39.1158 | 1 | 0 | Region_4 | Envicool 3000W | Open
SQR0384 | 20.6292 | 40.6963 | 1 | 0 | Region_4 | Envicool 3000W | Open
SQR0171 | 20.5306 | 40.6998 | 1 | 0 | Region_4 | Envicool 3000W | Open
JED2271 | 21.47717 | 39.26808 | 1 | 0 | Region_4 | Envicool 3000W | Open
HJR0019 | 20.252533 | 41.085701 | 1 | 0 | Region_4 | Envicool 3000W | Open
USF0237 | 21.9278 | 39.3047 | 1 | 0 | Region_4 | Envicool 3000W | Open
JED0782 | 21.4423 | 39.2808 | 1 | 0 | Region_4 | Envicool 3000W | Open
TAF2362 | 21.2391 | 40.4012 | 1 | 0 | Region_4 | Envicool 3000W | Open
JED0947 | 21.2594 | 39.1858 | 1 | 0 | Region_4 | Envicool 3000W | Open
JED0415 | 21.5356 | 39.1657 | 1 | 0 | Region_4 | Envicool 3000W | Open
AQA0018 | 20.3197219 | 41.1188783 | 1 | 0 | Region_4 | Envicool 3000W | Open
JED2060 | 21.5889 | 39.1379 | 1 | 0 | Region_4 | Envicool 3000W | Open
BIK0150 | 20.8501 | 39.6055 | 1 | 0 | Region_4 | Envicool 3000W | Open
SQR2093 | 20.7052 | 40.6882 | 1 | 0 | Region_4 | Envicool 3000W | Open
JED0787 | 21.434 | 39.29 | 1 | 0 | Region_4 | Envicool 3000W | Open
JED0514 | 21.58805 | 39.1514 | 1 | 0 | Region_4 | Envicool 3000W | Open
JED2138 | 21.7787 | 39.2131 | 1 | 0 | Region_4 | Envicool 3000W | Open
DAF0476 | 22.0927 | 39.3135 | 1 | 0 | Region_4 | Envicool 3000W | Open
JED0056 | 21.29732 | 39.24032 | 1 | 0 | Region_4 | Envicool 3000W | Open
JED0742 | 21.6147 | 39.1868 | 1 | 0 | Region_4 | Envicool 3000W | Open
NNL0146 | 20.603 | 40.3382 | 1 | 0 | Region_4 | Envicool 3000W | Open
MLJI0166 | 20.6963 | 40.2769 | 1 | 0 | Region_4 | Envicool 3000W | Open
JED0188 | 21.7303 | 39.1072 | 1 | 0 | Region_4 | Envicool 3000W | Open
JED0832 | 21.5185 | 39.2588 | 1 | 0 | Region_4 | Envicool 3000W | Open
GMQ0153 | 20.24819 | 40.71932 | 1 | 0 | Region_4 | Envicool 3000W | Open
JED2577 | 21.707772 | 39.1125 | 1 | 0 | Region_4 | Envicool 3000W | Open
LTH2122 | 20.1407 | 40.271 | 1 | 0 | Region_4 | Envicool 3000W | Open
JED0880 | 21.7592 | 39.2166 | 1 | 0 | Region_4 | Envicool 3000W | Open
JED0900 | 21.783 | 39.1981 | 1 | 0 | Region_4 | Envicool 3000W | Open
SQR0076 | 20.6072653 | 40.6669319 | 1 | 0 | Region_4 | Envicool 3000W | Open
SQR0383 | 20.6455 | 40.8019 | 1 | 0 | Region_4 | Envicool 3000W | Open
JED0914 | 21.7892 | 39.1802 | 1 | 0 | Region_4 | Envicool 3000W | Open
JED2051 | 21.5751 | 39.1584 | 1 | 0 | Region_4 | Envicool 3000W | Open
JED2787 | 21.577596 | 39.127326 | 1 | 0 | Region_4 | Envicool 3000W | Open
QFF2446 | 21.8208 | 40.4558 | 1 | 0 | Region_4 | Envicool 3000W | Open
HJR0040 | 20.3144 | 40.9854 | 1 | 0 | Region_4 | Envicool 3000W | Open
JED0769 | 21.4732 | 39.1677 | 1 | 0 | Region_4 | Envicool 3000W | Open
JED0859 | 21.3939 | 39.2813 | 1 | 0 | Region_4 | Envicool 3000W | Open
JED2061 | 21.7533 | 39.0862 | 1 | 0 | Region_4 | Envicool 3000W | Open
UKZ0211 | 20.502 | 40.806 | 1 | 0 | Region_4 | Envicool 3000W | Open
JED0068 | 21.5645 | 39.1629 | 1 | 0 | Region_4 | Envicool 3000W | Open
NNL0176 | 20.3746 | 40.2072 | 1 | 0 | Region_4 | Envicool 3000W | Open
JED0804 | 21.4592 | 39.2095 | 1 | 0 | Region_4 | Envicool 3000W | Open
JED0792 | 21.4092 | 39.2571 | 1 | 0 | Region_4 | Envicool 3000W | Open
JED0865 | 21.7851 | 39.0923 | 1 | 0 | Region_4 | Envicool 3000W | Open
JED0220 | 21.6423 | 39.1396 | 1 | 0 | Region_4 | Envicool 3000W | Open
JED0490 | 21.3157 | 39.1638 | 1 | 0 | Region_4 | Envicool 3000W | Open
JED0771 | 21.4573 | 39.1702 | 1 | 0 | Region_4 | Envicool 3000W | Open
JED0881 | 21.7722 | 39.1042 | 1 | 0 | Region_4 | Envicool 3000W | Open
JED0921 | 21.4927 | 39.2836 | 1 | 0 | Region_4 | Envicool 3000W | Open
JED0145 | 21.5921 | 39.1099 | 1 | 0 | Region_4 | Envicool 3000W | Open
RAB2163 | 22.84811 | 39.02937 | 1 | 0 | Region_4 | Envicool 3000W | Open
TAF2361 | 21.2795 | 40.4412 | 1 | 0 | Region_4 | Envicool 3000W | Open
JED2130 | 21.59237 | 39.148268 | 1 | 0 | Region_4 | Envicool 3000W | Open
JED0306 | 21.5709604 | 39.2943643 | 1 | 0 | Region_4 | Envicool 3000W | Open
JED0934 | 21.593 | 39.1557 | 1 | 0 | Region_4 | Envicool 3000W | Open
JED2352 | 21.5805149 | 39.20893 | 1 | 0 | Region_4 | Envicool 3000W | Open
JED0920 | 21.6907 | 39.2087 | 1 | 0 | Region_4 | Envicool 3000W | Open
QUN0341 | 19.1292 | 41.0835 | 1 | 0 | Region_4 | Envicool 3000W | Open
JED0171 | 21.528 | 39.2177 | 1 | 0 | Region_4 | Envicool 3000W | Open
JED0048 | 21.5376 | 39.1695 | 1 | 0 | Region_4 | Envicool 3000W | Open
JED0215 | 21.5819 | 39.1935 | 1 | 0 | Region_4 | Envicool 3000W | Open
HAW2335 | 21.4398 | 40.4332 | 1 | 0 | Region_4 | Envicool 3000W | Open
JED0390 | 21.5051 | 39.2398 | 1 | 0 | Region_4 | Envicool 3000W | Open
JED0855 | 21.6595 | 39.2537 | 1 | 0 | Region_4 | Envicool 3000W | Open
JED0959 | 21.837 | 39.2392 | 1 | 0 | Region_4 | Envicool 3000W | Open
JED0899 | 21.2991 | 39.2508 | 1 | 0 | Region_4 | Envicool 3000W | Open
JED0924 | 21.7701 | 39.1619 | 1 | 0 | Region_4 | Envicool 3000W | Open
JED0739 | 21.5614 | 39.1831 | 1 | 0 | Region_4 | Envicool 3000W | Open
JED0751 | 21.546 | 39.2925 | 1 | 0 | Region_4 | Envicool 3000W | Open
HAW0877 | 21.43192 | 40.45138 | 1 | 0 | Region_4 | Envicool 3000W | Open
JED0993 | 21.61064 | 39.185116 | 1 | 0 | Region_4 | Envicool 3000W | Open
JED0882 | 21.6123 | 39.2379 | 1 | 0 | Region_4 | Envicool 3000W | Open
JED2029 | 21.62135 | 39.17472 | 1 | 0 | Region_4 | Envicool 3000W | Open
MAS0030 | 23.1486 | 39.1374 | 1 | 0 | Region_4 | Envicool 3000W | Open
RAB0966 | 22.826 | 39.0501 | 1 | 0 | Region_4 | Envicool 3000W | Open
JED2074 | 21.58052 | 39.25031 | 1 | 0 | Region_4 | Envicool 3000W | Open
JED2131 | 21.6188 | 39.2084 | 1 | 0 | Region_4 | Envicool 3000W | Open
HHR0469 | 21.7595 | 39.1835 | 1 | 0 | Region_4 | Envicool 3000W | Open
JED0404 | 21.3847 | 39.3515 | 1 | 0 | Region_4 | Envicool 3000W | Open
MLJI0143 | 20.7688 | 40.2634 | 1 | 0 | Region_4 | Envicool 3000W | Open
NOB0035 | 22.8949 | 39.2505 | 1 | 0 | Region_4 | Envicool 3000W | Open
KUL0006 | 22.514059 | 39.303633 | 1 | 0 | Region_4 | Envicool 3000W | Open
JED2039 | 21.5504 | 39.2943 | 1 | 0 | Region_4 | Envicool 3000W | Open
JED2026 | 21.7694 | 39.0849 | 1 | 0 | Region_4 | Envicool 3000W | Open
UKZ0243 | 20.3907 | 40.9362 | 1 | 0 | Region_4 | Envicool 3000W | Open
SIR0173 | 20.236073 | 40.9121314 | 1 | 0 | Region_4 | Envicool 3000W | Open
JED2040 | 21.568 | 39.1594 | 1 | 0 | Region_4 | Envicool 3000W | Open
HAW2118 | 21.4495 | 40.4429 | 1 | 0 | Region_4 | Envicool 3000W | Open
YLM0789 | 20.8619707 | 40.3656486 | 1 | 0 | Region_4 | Envicool 3000W | Open
YLM0745 | 20.8893117 | 40.365708 | 1 | 0 | Region_4 | Envicool 3000W | Open
MLJI0187 | 20.7152 | 40.5516 | 1 | 0 | Region_4 | Envicool 3000W | Open
JED2255 | 21.75723 | 39.073654 | 1 | 0 | Region_4 | Envicool 3000W | Open
JED2184 | 21.62439 | 39.18726 | 1 | 0 | Region_4 | Envicool 3000W | Open
JED2045 | 21.4758 | 39.2159 | 1 | 0 | Region_4 | Envicool 3000W | Open
JED2145 | 21.6035 | 39.2619 | 1 | 0 | Region_4 | Envicool 3000W | Open
JED0891 | 21.4994 | 39.3569 | 1 | 0 | Region_4 | Envicool 3000W | Open
JED2162 | 21.692412 | 39.105594 | 1 | 0 | Region_4 | Envicool 3000W | Open
JED0085 | 21.5376 | 39.2201 | 1 | 0 | Region_4 | Envicool 3000W | Open
JED2021 | 21.5902 | 39.2738 | 1 | 0 | Region_4 | Envicool 3000W | Open
TAF0267 | 21.2968 | 40.4387 | 1 | 0 | Region_4 | Envicool 3000W | Open
JED0118 | 21.6324 | 39.1505 | 1 | 0 | Region_4 | Envicool 3000W | Open
TAF2272 | 21.7551 | 40.651 | 1 | 0 | Region_4 | Envicool 3000W | Open
MAK0629 | 21.4008 | 39.7446 | 1 | 0 | Region_5 | Envicool 3000W | Open
HAS0707 | 21.3162 | 39.8732 | 1 | 0 | Region_5 | Envicool 3000W | Open
HAJ0230 | 21.3754 | 39.9876 | 1 | 0 | Region_5 | Envicool 3000W | Open
MAK0665 | 21.4332 | 39.6296 | 1 | 0 | Region_5 | Envicool 3000W | Open
QUR0341 | 21.308 | 40.0573 | 1 | 0 | Region_5 | Envicool 3000W | Open
MAK0828 | 21.4245 | 39.7687 | 1 | 0 | Region_5 | Envicool 3000W | Open
MAK0754 | 21.4539 | 39.9735 | 1 | 0 | Region_5 | Envicool 3000W | Open
MAK0221 | 21.4445 | 39.8525 | 1 | 0 | Region_5 | Envicool 3000W | Open
MAK0814 | 21.3742 | 39.8364 | 1 | 0 | Region_5 | Envicool 3000W | Open
MAK0131 | 21.4294 | 39.7903 | 1 | 0 | Region_5 | Envicool 3000W | Open
MAK0206 | 21.4019 | 39.8675 | 1 | 0 | Region_5 | Envicool 3000W | Open
MAK0681 | 21.3865 | 39.8787 | 1 | 0 | Region_5 | Envicool 3000W | Open
MAK2227 | 21.42162 | 39.83484 | 1 | 0 | Region_5 | Envicool 3000W | Open
MAK0758 | 21.3571 | 39.7886 | 1 | 0 | Region_5 | Envicool 3000W | Open
MAK0982 | 21.3854 | 39.8751 | 1 | 0 | Region_5 | Envicool 3000W | Open
JURY0904 | 21.6864673 | 39.7332717 | 1 | 0 | Region_5 | Envicool 3000W | Open
MAK0667 | 21.6041 | 39.824 | 1 | 0 | Region_5 | Envicool 3000W | Open
MAK0639 | 21.3785 | 39.7951 | 1 | 0 | Region_5 | Envicool 3000W | Open
MUL0363 | 21.7725 | 40.3459 | 1 | 0 | Region_5 | Envicool 3000W | Open
MAK0637 | 21.3646 | 39.8081 | 1 | 0 | Region_5 | Envicool 3000W | Open
MAK2084 | 21.528 | 39.7776 | 1 | 0 | Region_5 | Envicool 3000W | Open
MAK0321 | 21.4213 | 39.8545 | 1 | 0 | Region_5 | Envicool 3000W | Open
MAK0690 | 21.3741 | 39.8115 | 1 | 0 | Region_5 | Envicool 3000W | Open
MAK2307 | 21.4132 | 39.8602 | 1 | 0 | Region_5 | Envicool 3000W | Open
MAK0051 | 21.4603 | 39.9634 | 1 | 0 | Region_5 | Envicool 3000W | Open
MAK2257 | 21.5704 | 39.77888 | 1 | 0 | Region_5 | Envicool 3000W | Open
MAK0200 | 21.6197 | 39.7921 | 1 | 0 | Region_5 | Envicool 3000W | Open
MAK0273 | 21.4484 | 39.9248 | 1 | 0 | Region_5 | Envicool 3000W | Open
MAK0698 | 21.468 | 39.9359 | 1 | 0 | Region_5 | Envicool 3000W | Open
MAK2211 | 21.363569 | 39.834903 | 1 | 0 | Region_5 | Envicool 3000W | Open
MAK0945 | 21.4862 | 39.9449 | 1 | 0 | Region_5 | Envicool 3000W | Open
MAK0755 | 21.4555 | 39.9282 | 1 | 0 | Region_5 | Envicool 3000W | Open
MAK0254 | 21.4404 | 39.8127 | 1 | 0 | Region_5 | Envicool 3000W | Open
OMQ0633 | 21.3197 | 39.5891 | 1 | 0 | Region_5 | Envicool 3000W | Open
MAK0826 | 21.5618 | 39.9541 | 1 | 0 | Region_5 | Envicool 3000W | Open
MLK0699 | 21.1942 | 40.0004 | 1 | 0 | Region_5 | Envicool 3000W | Open
MAK2237 | 21.3815 | 39.77763 | 1 | 0 | Region_5 | Envicool 3000W | Open
MAK0618 | 21.528 | 40.0183 | 1 | 0 | Region_5 | Envicool 3000W | Open
MAK0627 | 21.4385 | 39.7611 | 1 | 0 | Region_5 | Envicool 3000W | Open
MAK0121 | 21.5613 | 39.7765 | 1 | 0 | Region_5 | Envicool 3000W | Open
MAK0676 | 21.3758 | 39.7649 | 1 | 0 | Region_5 | Envicool 3000W | Open
MAK0645 | 21.4363 | 39.8489 | 1 | 0 | Region_5 | Envicool 3000W | Open
MAK2230 | 21.408 | 39.8328 | 1 | 0 | Region_5 | Envicool 3000W | Open
MAK2100 | 21.3474965 | 39.7931 | 1 | 0 | Region_5 | Envicool 3000W | Open
MAK0259 | 21.3948 | 39.8828 | 1 | 0 | Region_5 | Envicool 3000W | Open
HRT0139 | 21.2896 | 40.2021 | 1 | 0 | Region_5 | Envicool 3000W | Open
MAK0710 | 21.2877 | 39.8342 | 1 | 0 | Region_5 | Envicool 3000W | Open
MAK0816 | 21.3976 | 39.8782 | 1 | 0 | Region_5 | Envicool 3000W | Open
MAK2089 | 21.4004 | 39.8641 | 1 | 0 | Region_5 | Envicool 3000W | Open
MAK0064 | 21.4225 | 39.8521 | 1 | 0 | Region_5 | Envicool 3000W | Open
MAK0083 | 21.3864 | 39.8903 | 1 | 0 | Region_5 | Envicool 3000W | Open
MAK0138 | 21.454139 | 40.043754 | 1 | 0 | Region_5 | Envicool 3000W | Open
MAK0194 | 21.3995 | 39.7846 | 1 | 0 | Region_5 | Envicool 3000W | Open
MAK0081 | 21.5011 | 39.7835 | 1 | 0 | Region_5 | Envicool 3000W | Open
MAK0214 | 21.4403 | 39.795 | 1 | 0 | Region_5 | Envicool 3000W | Open
MAK0216 | 21.4591 | 39.8809 | 1 | 0 | Region_5 | Envicool 3000W | Open
MAK0088 | 21.4684 | 39.9673 | 1 | 0 | Region_5 | Envicool 3000W | Open
MAK0386 | 21.3637 | 39.6256 | 1 | 0 | Region_5 | Envicool 3000W | Open
MAK0461 | 21.3709 | 39.8776 | 1 | 0 | Region_5 | Envicool 3000W | Open
MAK0616 | 21.352 | 39.899 | 1 | 0 | Region_5 | Envicool 3000W | Open
MAK0630 | 21.3929 | 39.7801 | 1 | 0 | Region_5 | Envicool 3000W | Open
MAK0655 | 21.2728 | 39.9958 | 1 | 0 | Region_5 | Envicool 3000W | Open
MAK0103 | 21.4793 | 39.9376 | 1 | 0 | Region_5 | Envicool 3000W | Open
MAK0666 | 21.4103 | 39.7077 | 1 | 0 | Region_5 | Envicool 3000W | Open
MAK0671 | 21.5808 | 39.7715 | 1 | 0 | Region_5 | Envicool 3000W | Open
MAK0674 | 21.3039 | 39.9887 | 1 | 0 | Region_5 | Envicool 3000W | Open
MAK0688 | 21.3568 | 39.7919 | 1 | 0 | Region_5 | Envicool 3000W | Open
MAK0713 | 21.4445 | 39.8628 | 1 | 0 | Region_5 | Envicool 3000W | Open
MAK0751 | 21.3712 | 39.7921 | 1 | 0 | Region_5 | Envicool 3000W | Open
MAK0625 | 21.4881 | 39.9328 | 1 | 0 | Region_5 | Envicool 3000W | Open
MAK0730 | 21.3973 | 39.6206 | 1 | 0 | Region_5 | Envicool 3000W | Open
MAK0628 | 21.4062 | 39.7752 | 1 | 0 | Region_5 | Envicool 3000W | Open
MAK0640 | 21.5026 | 39.7635 | 1 | 0 | Region_5 | Envicool 3000W | Open
MAK0811 | 21.4473 | 39.8374 | 1 | 0 | Region_5 | Envicool 3000W | Open
MAK0817 | 21.4034 | 39.7856 | 1 | 0 | Region_5 | Envicool 3000W | Open
MAK0819 | 21.4292 | 39.8598 | 1 | 0 | Region_5 | Envicool 3000W | Open
MAK0821 | 21.3692 | 39.8301 | 1 | 0 | Region_5 | Envicool 3000W | Open
MAK0825 | 21.46709 | 39.9493 | 1 | 0 | Region_5 | Envicool 3000W | Open
MAK0838 | 21.502348 | 39.886251 | 1 | 0 | Region_5 | Envicool 3000W | Open
MAK0884 | 21.3655 | 39.83101 | 1 | 0 | Region_5 | Envicool 3000W | Open
MAK0928 | 21.397769 | 39.777114 | 1 | 0 | Region_5 | Envicool 3000W | Open
MAK0929 | 21.35218 | 39.78969 | 1 | 0 | Region_5 | Envicool 3000W | Open
MAK0936 | 21.4008 | 39.7912 | 1 | 0 | Region_5 | Envicool 3000W | Open
MAK0944 | 21.4023 | 39.7133 | 1 | 0 | Region_5 | Envicool 3000W | Open
MAK0981 | 21.5142 | 39.7836 | 1 | 0 | Region_5 | Envicool 3000W | Open
MAK0983 | 21.3559 | 39.8721 | 1 | 0 | Region_5 | Envicool 3000W | Open
MAK2079 | 21.4412 | 39.8228 | 1 | 0 | Region_5 | Envicool 3000W | Open
MAK2080 | 21.493475 | 39.959717 | 1 | 0 | Region_5 | Envicool 3000W | Open
MAK2081 | 21.4745 | 39.9404 | 1 | 0 | Region_5 | Envicool 3000W | Open
MAK2086 | 21.465 | 39.9365 | 1 | 0 | Region_5 | Envicool 3000W | Open
MAK2091 | 21.501759 | 39.950138 | 1 | 0 | Region_5 | Envicool 3000W | Open
MAK2099 | 21.3791 | 39.7906 | 1 | 0 | Region_5 | Envicool 3000W | Open
MAK2301 | 21.400589 | 39.876815 | 1 | 0 | Region_5 | Envicool 3000W | Open
MLK0685 | 21.193 | 39.9629 | 1 | 0 | Region_5 | Envicool 3000W | Open
MLK0707 | 21.1908 | 39.9463 | 1 | 0 | Region_5 | Envicool 3000W | Open
MLK0725 | 21.1815 | 39.9257 | 1 | 0 | Region_5 | Envicool 3000W | Open
OMQ0701 | 21.2864 | 39.5907 | 1 | 0 | Region_5 | Envicool 3000W | Open
OMQ0724 | 21.3017 | 39.568 | 1 | 0 | Region_5 | Envicool 3000W | Open
OMQ0802 | 21.3102 | 39.552 | 1 | 0 | Region_5 | Envicool 3000W | Open
OMQ0804 | 21.3076 | 39.5117 | 1 | 0 | Region_5 | Envicool 3000W | Open
MAK0648 | 21.3512 | 39.7953 | 1 | 0 | Region_5 | Envicool 3000W | Open
MAK0725 | 21.4292 | 39.8344 | 1 | 0 | Region_5 | Envicool 3000W | Open
MAK2088 | 21.417502 | 39.829215 | 1 | 0 | Region_5 | Envicool 3000W | Open

## Dependency GAP
Site ID | Region | Category | Comments